## Team-data
Team - data | Fill inn names for each team-member and adjust activities and categories according to your team needs in the project
| Name - team-members | Activities | Categories
| John Ivar | Self-education | Documentation
| Håkon | Information search | Adminstration
| Lotte | User testing | Quality assurance
| Birthe | Prototyping | Wireframe
| Vemund | Coding | MVP
|  | Testing of code | Final delivery
|  | Error correction | Leave
|  | Project reporting | Beta Client (MMP)
|  | Presentation including preparation | Releasae Candidate
|  | Team meetings | Sick
Team meetings with supervisor
Illness or leave
Meeting client
Approved leave of absence
Add your activities

## Summary
Summary of timesheets for project:
Week no | John Ivar | Håkon | Lotte | Birthe | Vemund | Sum hours week
Week 4 | 4 | 4 | 4 | 4 | 4 | 20
Week 5 | 2 | 2 | 2 | 3 | 2 | 11
Week 6 | 2.5 | 2.5 | 1.5 | 1.5 | 2.5 | 10.5
Week 7 | 6 | 6 | 6 | 6 | 6 | 30
Week 8 | 17.5 | 12.5 | 12 | 12.5 | 12.5 | 67
Week 9 | 12 | 6 | 6 | 13 | 6 | 43
Week 10 | 4 | 4 | 4 | 5 | 4 | 21
Week 11 | 19 | 19 | 22 | 19 | 19 | 98
Week 12 | 22 | 14 | 13 | 14.5 | 14 | 77.5
Week 13 | 15.5 | 8 | 10 | 11 | 5 | 49.5
Week 14 | 9.5 | 2 | 4.5 | 2 | 0 | 18
Week 15 | 25.5 | 10 | 14 | 11 | 13 | 73.5
Week 16 | 31.5 | 28 | 20.5 | 16.5 | 26.5 | 123
Week 17 | 12.5 | 0.5 | 9 | 15 | 9 | 46
Total sum hours pr person | 183.5 | 118.5 | 128.5 | 134 | 123.5 | 427.5
Total sum hours pr person excluded illness and leave | 183.5 | 108.5 | 128.5 | 134 | 123.5 | 417.5
Summary of hours by activity
Activity | John Ivar | Håkon | Lotte | Birthe | Vemund | Total sum hours pr activity
Self-education |  |  |  | 0.5 |  | 0.5
Information search |  |  |  | 5.5 |  | 5.5
User testing |  |  |  | 1 |  | 1
Prototyping |  |  |  | 57.5 |  | 57.5
Coding |  |  |  | 6.5 |  | 6.5
Testing of code | [5 empty] | 0
Error correction | [5 empty] | 0
Project reporting |  |  |  | 42.5 |  | 42.5
Presentation including preparation | [5 empty] | 0
Team meetings |  |  |  | 4.5 |  | 4.5
Team meetings with supervisor |  |  |  | 1 |  | 1
Illness or leave |  | 10 |  |  |  | 10
Meeting client | [5 empty] | 0
Add your activities | [5 empty] | 0
Total sum hours | 0 | 10 | 0 | 119 | 0 | 129
Summary of hours by category
Category | John Ivar | Håkon | Lotte | Birthe | Vemund | Total sum hours pr category
Documentation |  |  |  | 47 |  | 47
Adminstration |  |  |  | 5.5 |  | 5.5
Quality assurance | [5 empty] | 0
Wireframe | [5 empty] | 0
MVP |  |  |  | 43 |  | 43
Final delivery | [5 empty] | 0
Leave | [5 empty] | 0
Beta Client (MMP) |  |  |  | 18.5 |  | 18.5
Releasae Candidate |  |  |  | 5 |  | 5
Total sum hours | 0 | 0 | 0 | 119 | 0 | 119

## Uke 4
Timesheet with weekly status report |  |  | Time | Date | Weekly status report
With each weekly time list, a status report (log) must be included that shows what activities each team member has completed during this week. These include a description of the following:
Timesheet |  | John Ivar |  |  | A short description of the nature of the work and which results are achieved.
Activity | Category | Duration (hours) |  |  | if problems have occured, describe the problems and what steps are/ need to be taken to correct the situation
Project reporting | Documentation | 4 |  |  | Started with the collaborationg agreement
Week 4 |  | 4
Timesheet |  | Håkon
Activity | Category | Duration (hours)
Project reporting | Documentation | 4 |  |  | Started with the collaborationg agreement
Week 4 |  | 4
Timesheet |  | Lotte
Activity | Category | Duration (hours)
Project reporting | Documentation | 4 |  |  | Started with the collaborationg agreement
Week 4 |  | 4
Timesheet |  | Birthe
Activity | Category | Duration (hours)
Project reporting | Documentation | 4 |  |  | Started with the collaborationg agreement
Week 4 |  | 4
Timesheet |  | Vemund
Activity | Category | Duration (hours)
Illness |  | 4
Week 4 |  | 4
Timesheet |  | 0
Activity | Category | Duration (hours)
Week 4 |  | 0

## Uke 5
Timesheet with weekly status report |  |  | Time | Date | Weekly status report
Timesheet |  | John Ivar
Activity | Category | Duration (hours)
Team meetings | Adminstration | 2 |  |  | Administration for the upcomming project
Week 5 |  | 2
Timesheet |  | Håkon
Activity | Category | Duration (hours)
Team meetings | Adminstration | 2 |  |  | Administration for the upcomming project
Week 5 |  | 2
Timesheet |  | Lotte
Activity | Category | Duration (hours)
Team meetings | Adminstration | 2 |  |  | Administration for the upcomming project
Week 5 |  | 2
Timesheet |  | Birthe
Activity | Category | Duration (hours)
Team meetings | Adminstration | 2 |  |  | Administration for the upcomming project
Project reporting | Documentation | 1 |  |  | Coolaboration agreement
Week 5 |  | 3
Timesheet |  | Vemund
Aktivitet | Kategori | Antall timer
Team meetings | Adminstration | 2 |  |  | Administration for the upcomming project
Week 5 |  | 2
Timesheet |  | 0
Activity | Category | Duration (hours)
Week 5 |  | 0

## Uke 6
Timesheet with weekly status report |  |  | Time | Date | Weekly status report
Timesheet |  | John Ivar
Activity | Category | Duration (hours)
Team meetings | Adminstration | 1.5 |  |  | Started Scrum. Divided roles and set up issueboard. Discussed the application
Meeting client | Documentation | 1 |  |  | First meeting with client
Week 6 |  | 2.5
Timesheet |  | Håkon
Activity | Category | Duration (hours)
Team meetings | Adminstration | 1.5 |  |  | Started Scrum. Divided roles and set up issueboard. Discussed the application
Meeting client | Documentation | 1 |  |  | First meeting with client
Week 6 |  | 2.5
Timesheet |  | Lotte
Activity | Category | Duration (hours)
Team meetings | Adminstration | 1.5 |  |  | Started Scrum. Divided roles and set up issueboard. Discussed the application
Week 6 |  | 1.5
Timesheet |  | Birthe
Activity | Category | Duration (hours)
Team meetings | Adminstration | 1.5 |  |  | Started Scrum. Divided roles and set up issueboard. Discussed the application
Week 6 |  | 1.5
Timesheet |  | Vemund
Activity | Category | Duration (hours)
Team meetings | Adminstration | 1.5 |  |  | Started Scrum. Divided roles and set up issueboard. Discussed the application
Meeting client | Documentation | 1 |  |  | First meeting with client
Week 6 |  | 2.5
Timesheet |  | 0
Activity | Category | Duration (hours)
Week 6 |  | 0

## Uke 7
Timesheet with weekly status report |  |  | Time | Date | Weekly status report
Timesheet |  | John Ivar
Activity | Category | Duration (hours)
Project reporting | Documentation | 6 |  |  | Vision Document
Week 7 |  | 6
Timesheet |  | Håkon
Activity | Category | Duration (hours)
Project reporting | Documentation | 6 |  |  | Wireframes
Week 7 |  | 6
Timesheet |  | Lotte
Activity | Category | Duration (hours)
Project reporting | Documentation | 6 |  |  | Vision Document
Week 7 |  | 6
Timesheet |  | Birthe
Activity | Category | Duration (hours)
Project reporting | Documentation | 6 |  |  | Vision Document
Week 7 |  | 6
Timesheet |  | Vemund
Activity | Category | Duration (hours)
Project reporting | Documentation | 6 |  |  | Wireframes
Week 7 |  | 6
Timesheet |  | 0
Activity | Category | Duration (hours)
Week 7 |  | 0

## Uke 8
Timesheet with weekly status report |  |  | Time | Date | Weekly status report
Timesheet |  | John Ivar
Activity | Category | Duration (hours)
Team meetings | Adminstration | 0.5 |  | 2023-02-20 | Meeting with TA.
Project reporting | Documentation | 6 |  | 2023-02-20 | Vision document. Administration. Client meeting.
Project reporting | Documentation | 6 |  | 2023-02-22 | Vision document. Administration.
Project reporting | Adminstration | 1 |  | 2023-02-26 | Gantt diagram.
Illness | Leave | 4
Week 8 |  | 17.5
Timesheet |  | Håkon
Activity | Category | Duration (hours)
Team meetings | Adminstration | 0.5 |  | 2023-02-20 | Meeting with TA.
Prototyping | Wireframe | 6 |  | 2023-02-20 | Wireframe. Client meeting.
Prototyping | Wireframe | 6 |  | 2023-02-22 | Wireframe. Domain model. Class diagram.
Week 8 |  | 12.5
Timesheet |  | Lotte
Aktivitet | Kategori | Antall timer
Approved leave of absence | Leave |  |  | 2023-02-20 | Approved leave of absence.
Project reporting | Documentation | 6 |  | 2023-02-22 | Vision document.
Project reporting | Documentation | 6 |  | 2023-02-26 | Vision document.
Week 8 |  | 12
Timesheet |  | Birthe
Activity | Category | Duration (hours)
Team meetings | Adminstration | 0.5 |  | 2023-02-20 | Meeting with TA.
Project reporting | Documentation | 6 |  | 2023-02-20 | Vision document. Client meeting.
Project reporting | Documentation | 6 |  | 2023-02-22 | Vision document.
Week 8 |  | 12.5
Timesheet |  | Vemund
Activity | Category | Duration (hours)
Team meetings | Adminstration | 0.5 |  | 2023-02-20 | Meeting with TA.
Prototyping | Wireframe | 6 |  | 2023-02-20 | Wireframe. Client meeting.
Prototyping | Wireframe | 6 |  | 2023-02-22 | Wireframe. Domain model. Class diagram.
Week 8 |  | 12.5
Timesheet |  | 0
Activity | Category | Duration (hours)
Week 8 |  | 0

## Uke 9
Timesheet with weekly status report |  |  | Time | Date | Weekly status report
Timesheet |  | John Ivar
Activity | Category | Duration (hours)
Project reporting | Documentation | 2 |  | 2023-02-27 | Review first draft of vision document.
Team meetings | Adminstration | 0.5 |  | 2023-02-27 | Meeting with TA.
Prototyping | MVP | 3.5 |  | 2023-02-27 | Start coding. All participated in startup coding.
Self-education | MVP | 4 |  | 2023-03-01 | Trying to learn Scene Builder (fxml) - Campus
Self-education | MVP | 2 |  | 2023-03-01 | Trying to learn Scene Builder (fxml) - Homework
Week 9 |  | 12
Timesheet |  | Håkon
Activity | Category | Duration (hours)
Prototyping | MVP | 2 |  | 2023-02-27 | Class diagram and plan start of coding.
Team meetings | Adminstration | 0.5 |  | 2023-02-27 | Meeting with TA.
Prototyping | MVP | 3.5 |  | 2023-02-27 | Start coding. All participated in startup coding.
Week 9 |  | 6
Timesheet |  | Lotte
Activity | Category | Duration (hours)
Project reporting | Documentation | 2 |  | 2023-02-27 | Review first draft of vision document.
Team meetings | Adminstration | 0.5 |  | 2023-02-27 | Meeting with TA.
Prototyping | MVP | 3.5 |  | 2023-02-27 | Start coding. All participated in startup coding.
Week 9 |  | 6
Timesheet |  | Birthe
Activity | Category | Duration (hours)
Project reporting | Documentation | 4.5 |  | 2023-02-27 | Review first draft of vision document.
Team meetings | Adminstration | 0.5 |  | 2023-02-27 | Meeting with TA.
Prototyping | MVP | 5 |  | 2023-02-27 | Start coding. All participated in startup coding.
Project reporting | Documentation | 3 |  | 2023-03-05 | Vision document.
Week 9 |  | 13
Timesheet |  | Vemund
Activity | Category | Duration (hours)
Prototyping | Documentation | 2 |  | 2023-02-27 | Class diagram and plan start of coding.
Team meetings | Adminstration | 0.5 |  | 2023-02-27 | Meeting with TA.
Prototyping | MVP | 3.5 |  | 2023-02-27 | Start coding. All participated in startup coding.
Week 9 |  | 6
Timesheet |  | 0
Activity | Category | Duration (hours)
Week 9 |  | 0

## Uke 10
Timesheet with weekly status report |  |  | Time | Date | Weekly status report
Timesheet |  | John Ivar
Activity | Category | Duration (hours)
Prototyping | MVP | 4 |  | 2023-03-06 | MVP
Week 10 |  | 4
Timesheet |  | Håkon
Activity | Category | Duration (hours)
Prototyping | MVP | 4 |  | 2023-03-06 | MVP
Week 10 |  | 4
Timesheet |  | Lotte
Activity | Category | Duration (hours)
Prototyping | MVP | 4 |  | 2023-03-06 | MVP
Week 10 |  | 4
Timesheet |  | Birthe
Activity | Category | Duration (hours)
Prototyping | MVP | 4 |  | 2023-03-06 | MVP
Prototyping | MVP | 1
Week 10 |  | 5
Timesheet |  | Vemund
Activity | Category | Duration (hours)
Prototyping | MVP | 4 |  | 2023-03-06 | MVP
Week 10 |  | 4
Timesheet |  | 0
Activity | Category | Duration (hours)
Week 10 |  | 0

## Uke 11
Timesheet with weekly status report |  |  | Time | Date | Weekly status report
Timesheet |  | John Ivar
Activity | Category | Duration (hours)
Prototyping | MVP | 5.5 |  | 2023-03-13 | Working on GUI for MVP.
Team meetings with supervisor | Adminstration | 0.5 |  | 2023-03-13 | Guidance meeting 1.
Prototyping | MVP | 5 |  | 2023-03-15 | Working on GUI for MVP. SceneBuilder, dashboard and settings.
Prototyping | MVP | 8 |  | 2023-03-17 | Working on GUI for MVP. SceneBuilder, dashboard and settings. 0830-1630
Week 11 |  | 19
Timesheet |  | Håkon
Activity | Category | Duration (hours)
Prototyping | MVP | 5.5 |  | 2023-03-13 | Working on GUI for MVP.
Team meetings with supervisor | Adminstration | 0.5 |  | 2023-03-13 | Guidance meeting 1.
Prototyping | MVP | 5 |  | 2023-03-15
Prototyping | MVP | 8 |  | 2023-03-17
Week 11 |  | 19
Timesheet |  | Lotte
Activity | Category | Duration (hours)
Prototyping | MVP | 5.5 |  | 2023-03-13 | Working on GUI for MVP.
Team meetings with supervisor | Adminstration | 0.5 |  | 2023-03-13 | Guidance meeting 1.
Prototyping | MVP | 5 |  | 2023-03-15
Self-education | MVP | 3 |  | 2023-03-16 | Watched Scenebuilder tutorials
Prototyping | MVP | 8 |  | 2023-03-17
Week 11 |  | 22
Timesheet |  | Birthe
Activity | Category | Duration (hours)
Prototyping | MVP | 5.5 |  | 2023-03-13 | Working on GUI for MVP.
Team meetings with supervisor | Adminstration | 0.5 |  | 2023-03-13 | Guidance meeting 1.
Prototyping | MVP | 5 |  | 2023-03-15
Prototyping | MVP | 8 |  | 2023-03-17
Week 11 |  | 19
Timesheet |  | Vemund
Activity | Category | Duration (hours)
Prototyping | MVP | 5.5 |  | 2023-03-13 | Working on GUI for MVP.
Team meetings with supervisor | Adminstration | 0.5 |  | 2023-03-13 | Guidance meeting 1.
Prototyping | MVP | 5 |  | 2023-03-15
Prototyping | MVP | 8 |  | 2023-03-17
Week 11 |  | 19
Timesheet |  | 0
Activity | Category | Duration (hours)
Week 11 |  | 0

## Uke 12
Timesheet with weekly status report |  |  | Time | Date | Weekly status report
Timesheet |  | John Ivar
Activity | Category | Duration (hours)
Prototyping | MVP | 6 | kl 10-16 | 2023-03-20 | GUI for MVP. Controllers for FXML pages.
Prototyping | MVP | 3 | kl 09-12 | 2023-03-21 | GUI for MVP. Tied Controllers to FXML pages on Settings > New/Edit Category. Also worked on Dashboard controllers.
Prototyping | MVP | 6 | kl 08-14 | 2023-03-22 | Finished MVP. Tied controllers to Dashboard page and finished it with help from Vemund. Some controls on Settings.
Activities | Documentation | 2 | kl 09-11 | 1900-01-23 00:43 | Worked on Gitlab Wiki, specifically user test documents. Structuring wiki accordingly.
Activities | Documentation | 3 | kl 13-16 | 2023-03-24 | User Test documents formatting. Definitions for Technical Competence levels. Procrastination Blackbelt!
User testing | MVP | 1 | kl 17-18 | 2023-03-24 | MVP User Test and documentation.
User testing | MVP | 1 | kl 18-19 | 2023-03-26 | MVP User Test and documentation.
Week 12 |  | 22
Timesheet |  | Håkon
Activity | Category | Duration (hours)
Prototyping | MVP | 7 |  | 2023-03-20 | GUI for MVP. Controllers for FXML pages.
Prototyping | MVP | 6 |  | 2023-03-22 | Finished MVP. Worked on finishing Budget view.
User testing | MVP | 1 |  | 2023-03-23 | MVP User Test and documentation.
Week 12 |  | 14
Timesheet |  | Lotte
Activity | Category | Duration (hours)
Prototyping | MVP | 7 |  | 2023-03-20 | GUI for MVP. Controllers for FXML pages.
Prototyping | MVP | 6 |  | 2023-03-22 | Finished MVP. Worked on Wiki and main report.
Week 12 |  | 13
Timesheet |  | Birthe
Activity | Category | Duration (hours)
Prototyping | MVP | 7 |  | 2023-03-20 | GUI for MVP. Controllers for FXML pages.
Prototyping | MVP | 6 |  | 2023-03-22 | Finished MVP. Worked on Wiki and main report.
User testing | MVP | 1 |  | 2023-03-23 | MVP User Test and documentation.
Self-education | MVP | 0.5 |  | 2023-03-23 | Paths logo.
Week 12 |  | 14.5
Timesheet |  | Vemund
Activity | Category | Duration (hours)
Prototyping | MVP | 7 |  | 20.03.2023 | GUI for MVP. Controllers for FXML pages.
Prototyping | MVP | 6 |  | 2023-03-22 | Finished MVP. Worked on Dashboard and Budget view.
User testing | MVP | 1 |  | 2023-03-23 | MVP User Test and documentation.
Week 12 |  | 14
Timesheet |  | 0
Activity | Category | Duration (hours)
Week 12 |  | 0

## Uke 13
Timesheet with weekly status report |  |  | Time | Date | Weekly status report
Timesheet |  | John Ivar
Activity | Category | Duration (hours)
User testing | MVP | 1.5 | kl 0830-1000 | 2023-03-27 | Documentation of MVP user test from 26.03.2023
Team meetings with supervisor | Adminstration | 0.5 | kl 1015-1045 | 2023-03-27 | Guidance meeting 2.
Information search | Documentation | 5.5 | kl 1100-1630 | 2023-03-27 | Discussed feedback from MVP user test and feedback from guidance meeting. Listed priorities for further work.
Prototyping | Beta Client (MMP) | 5 | kl 0800-1400 | 2023-03-29 | Working on Release candidate, MMP (Minimum Marketable Product). Adapt GUI acc. to feedback and priorities
Project reporting | Documentation | 3 | kl 1000-1300 | 2023-04-02 | Report. Chapter 2 - Theory: Interaction Design, UX, UI, MMI, IA, UU.
Week 13 |  | 15.5
Timesheet |  | Håkon
Activity | Category | Duration (hours)
Team meetings with supervisor | Adminstration | 0.5 | kl 1015-1045 | 2023-03-27 | Guidance meeting 2.
Information search | Documentation | 1 | kl 1100-1200 | 2023-03-27 | Discussed feedback from MVP user test and feedback from guidance meeting. Listed priorities for further work.
Information search | Documentation | 1.5 | kl 1500-1630 | 2023-03-27
Prototyping | Release Candidate | 5 | kl 0800-1400 | 2023-03-29 | Working on Release candidate, MMP (Minimum Marketable Product).
Week 13 |  | 8
Timesheet |  | Lotte
Activity | Category | Duration (hours)
Team meetings with supervisor | Adminstration | 0.5 | kl 1015-1045 | 2023-03-27 | Guidance meeting 2.
Information search | Documentation | 5.5 | kl 1100-1630 | 2023-03-27 | Discussed feedback from MVP user test and feedback from guidance meeting. Listed priorities for further work.
Illness or leave | Leave | 4 |  | 2023-03-29 | Approved leave of abstence.
Week 13 |  | 10
Timesheet |  | Birthe
Activity | Category | Duration (hours)
Team meetings with supervisor | Adminstration | 0.5 | kl 1015-1045 | 2023-03-27 | Guidance meeting 2.
Information search | Documentation | 5.5 | kl 1100-1630 | 2023-03-27 | Discussed feedback from MVP user test and feedback from guidance meeting. Listed priorities for further work.
Prototyping | Release Candidate | 5 | kl 0800-1400 | 2023-03-29 | Working on Release candidate, MMP (Minimum Marketable Product).
Week 13 |  | 11
Timesheet |  | Vemund
Activity | Category | Duration (hours)
Team meetings with supervisor | Documentation |  |  | 2023-03-27 | Sick. Work from home, if up to it.
Prototyping | Release Candidate | 5 | kl 0800-1400 | 2023-03-29 | Working on Release candidate, MMP (Minimum Marketable Product).
Week 13 |  | 5
Timesheet |  | 0
Activity | Category | Duration (hours)
Week 13 |  | 0

## Uke 14
Timesheet with weekly status report |  |  | Time | Date | Weekly status report
Timesheet |  | John Ivar
Activity | Category | Duration (hours)
Project reporting | Documentation | 3 | kl 1000-1300 | 2023-04-03 | Report. Chapter 2 - Theory: Interaction Design, UX, UI, MMI, IA, UU.
Project reporting | Documentation | 3 | kl 1000-1300 | 2023-04-04 | Report. Chapter 2 - Theory: Interaction Design, UX, UI, MMI, IA, UU.
Prototyping | Beta Client (MMP) | 1 | kl 1100-1200 | 2023-04-05 | SceneBuilder. Update scenes based on MVP feedback. Receipt page, Settings page and Accounting page.
Prototyping | Beta Client (MMP) | 1.5 | kl 0930-1030 | 2023-04-07 | SceneBuilder. Worked on accountingPage, addAccountingEntry, addBudgetEntry, dashboardPage,
documentsPage (previously receiptsPage), settingsCategoryDialog and settingsPage.
Project reporting | Documentation | 1 | kl 1300-1400 | 2023-04-07 | Report. Chapter 2 - Theory: Interaction Design, UX, UI, MMI, IA, UU.
Week 14 |  | 9.5
Timesheet |  | Håkon
Activity | Category | Duration (hours)
Project reporting | Documentation | 2 |  | 2023-04-08 | Main report theory: System development methods
Week 14 |  | 2
Timesheet |  | Lotte
Activity | Category | Duration (hours)
User testing | MVP | 1 |  | 2023-04-06 | MVP User Test and documentation
Project reporting | Documentation | 3.5 |  | 2023-04-09 | Main report, Theory and relevant literature
Week 14 |  | 4.5
Timesheet |  | Birthe
Activity | Category | Duration (hours)
Project reporting | Documentation | 2 |  | 2023-04-09 | Main report theory: System development methods
Week 14 |  | 2
Timesheet |  | Vemund
Activity | Category | Duration (hours)
Week 14 |  | 0
Timesheet |  | 0
Activity | Category | Duration (hours)
Week 14 |  | 0

## Uke 15
Timesheet with weekly status report |  |  | Time | Date | Weekly status report
Timesheet |  | John Ivar
Activity | Category | Duration (hours)
User testing | MVP | 1 | kl 1100-1200 | 2023-04-10 | MVP User Test and documentation.
Prototyping | Beta Client (MMP) | 1 | kl 0830-0930 | 2023-04-11 | SceneBuilder. Worked on accountingPage,, dashboardPage and Settings page.
Prototyping | Beta Client (MMP) | 4 | kl 0800-1200 | 2023-04-12 | Tied controllers and buttons together with reworks of UI. AccountingPageController to populate tables (ongoing).
Prototyping | Beta Client (MMP) | 2 | kl 1200-1400 | 2023-04-12 | Reworked budgetPage (v3). Made alternate version of accountingPage (v3, buttons instead of tabs).
Prototyping | Beta Client (MMP) | 4 | kl 0830-1230 | 2023-04-13 | Worked on AccountingPageController to populate tables with data. FXML fine-tuning of values.
Prototyping | Beta Client (MMP) | 2 | kl 1530-1730 | 2023-04-13 | Worked on on AccountingPageController to populate tables with data.
Prototyping | Beta Client (MMP) | 7.5 | kl 0830-1600 | 2023-04-14 | Worked on AccountingPageController to populate tables with data. FXML fine-tuning of values and design.
Prototyping | Beta Client (MMP) | 4 | kl 0830-1230 | 2023-04-16 | Added Accessibility tags to all scenes. Added scene "aboutDialog".
Week 15 |  | 25.5
Timesheet |  | Håkon
Activity | Category | Duration (hours)
Illness |  | 4 |  | 2023-04-12 | Out sick.
Testing of code | Quality assurance | 6 | kl 1030-1630 | 2023-04-14 | Writing testing classes
Week 15 |  | 10
Timesheet |  | Lotte
Activity | Category | Duration (hours)
Project reporting | Beta Client (MMP) | 2 |  | 2023-04-10 | Main report, Introduction
Prototyping | Beta Client (MMP) | 6 | kl 0800-1300
Prototyping | Beta Client (MMP) | 6 | kl 1030-1630 | 2023-04-14
Week 15 |  | 14
Timesheet |  | Birthe
Activity | Category | Duration (hours)
Prototyping | Beta Client (MMP) | 5 | kl 0800-1300 |  | Validitation
Prototyping | Beta Client (MMP) | 6 | kl 1030-1500 | 2023-04-14 | GUI
Week 15 |  | 11
Timesheet |  | Vemund
Activity | Category | Duration (hours)
Prototyping | Beta Client (MMP) | 7 | kl 0800-1500
Prototyping | Beta Client (MMP) | 6 | kl 1030-1630 | 2023-04-14
Week 15 |  | 13
Timesheet |  | 0
Activity | Category | Duration (hours)
Week 15 |  | 0

## Uke 16
Timesheet with weekly status report |  |  | Time | Date | Weekly status report
Timesheet |  | John Ivar
Activity | Category | Duration (hours)
Coding | Beta Client (MMP) | 6.5 | kl 1000-1630 | 2023-04-17 | Fine-tuning FXML/GUI: budgetPage, accountingPage, sums.
Wiki: Started working on Universal Design, User Manual and Installation Manual pages.
Coding | Beta Client (MMP) | 2.5 | kl 0830-1100 | 2023-04-18 | FXML: Made v4 of budget and accounting (tabs, removed combobox). Hyperlink in About dialog.
Added logo banner to generalLayout. Fixed some bugs in settings FXML. Accessibility texts.
Project reporting | Documentation | 6 | kl 0800-1400 | 2023-04-19 | Wiki: UU, Wireframes and design. FXML: Fine-tuning and polish.
Project reporting | Documentation | 3 | kl 1300-1600 | 2023-04-20 | Wiki: Wireframes and design, Installation manual, Use Case Diagram
Project reporting | Documentation | 8 | kl 0800-1600 | 2023-04-21 | Wiki: Source code, Persistence, Unit Testing, Home, and others.
Project reporting | Documentation | 3 | kl 1000-1300 | 2023-04-23 | Wiki: User Manual.
Project reporting | Documentation | 2.5 | kl 1830-2100 | 2023-04-23 | Wiki: User Manual. Some code pruning. FXML tags.
Week 16 |  | 31.5
Timesheet |  | Håkon
Activity | Category | Duration (hours)
Coding | Beta Client (MMP) | 6.5 | kl 1000-1630 | 2023-04-17 | Writing test classes
Coding | Beta Client (MMP) | 4 | kl 1500-1900 | 2023-04-18 | Bug fixing
Self-education | Quality assurance | 1.5 | kl 2000-2130 | 2023-04-18 | Bug fixing
Self-education | Final delivery | 3.5 | kl 0800-1130 | 2023-04-19 | Researching test configuartion requirements
Coding | Quality assurance | 6.5 | kl 1130-1800 | 2023-04-19 | Writing test classes
Approved leave of absence | Leave | 6 | kl 1000-1600 | 2023-04-21 | Aproved leave for extracurricular activities
Week 16 |  | 28
Timesheet |  | Lotte
Activity | Category | Duration (hours)
Coding | Beta Client (MMP) | 6.5 | kl 1000-1630 | 2023-04-17
Coding | Beta Client (MMP) | 6 | kl 0800-1400 | 2023-04-19
Coding | Beta Client (MMP) | 3 | kl 1000-1300 | 2023-04-21
Project reporting | Documentation | 3 | kl 1300-1600 | 2023-04-21
Project reporting | Documentation | 1 |  | 2023-04-22 | Main report, Results
User testing | Final delivery | 1 |  | 2023-04-22 | Final Product User Test and Documentation
Week 16 |  | 20.5
Timesheet |  | Birthe
Activity | Category | Duration (hours)
Coding | Beta Client (MMP) | 6.5 | kl 1000-1630 | 2023-04-17
Project reporting | Documentation | 6 | kl 0800-1400 | 2023-04-19 | Organizing the main report
Project reporting | Documentation | 4 |  | 2023-04-24 | Main reprot: methods
Week 16 |  | 16.5
Timesheet |  | Vemund
Activity | Category | Duration (hours)
Coding | Beta Client (MMP) | 6.5 | kl 1000-1630 | 2023-04-17
Coding | Beta Client (MMP) | 6 | kl 0800-1400 | 2023-04-19
Coding | Beta Client (MMP) | 6 | kl 1000-1600 | 2023-04-21
Coding | Beta Client (MMP) | 4 | kl 1200-1600 | 2023-04-22
Coding | Beta Client (MMP) | 4 | kl 1400-1800 | 2023-04-23
Week 16 |  | 26.5
Timesheet |  | 0
Activity | Category | Duration (hours)
Week 16 |  | 0

## Uke 17
Timesheet with weekly status report |  |  | Time | Date | Weekly status report
Timesheet |  | John Ivar
Activity | Category | Duration (hours)
Team meetings | Adminstration | 0.5 |  | 2023-04-24 | Team meeting. Meeting with TA. Scrum meeting/Daily standup.
Project reporting | Documentation | 8.5 | kl 0830-1700 | 2023-04-24 | Wiki: Persistence, Unit Testing. Some editing of existing pages based on new final designs.
Project reporting | Final delivery | 1 | kl 0900-1000 | 2023-04-25 | Wiki: Finising touches.
Project reporting | Final delivery | 2.5 | kl 1000-1230 | 2023-04-25 | Report: Proof-reading and edits
|  |  | kl 22-2330 | 2023-04-25 | Wiki: Added details tags to show/hide code blocks. Report: Proof reading.
2023-04-26
Week 17 |  | 12.5
Timesheet |  | Håkon
Activity | Category | Duration (hours)
Team meetings | Adminstration | 0.5 |  | 2023-04-24 | Team meeting. Meeting with TA. Scrum meeting/Daily standup.
Project reporting | Documentation |  | kl 0830-hhmm | 2023-04-24
Week 17 |  | 0.5
Timesheet |  | Lotte
Activity | Category | Duration (hours)
Team meetings | Adminstration | 0.5 | kl 0800-0830 | 2023-04-24 | Team meeting. Meeting with TA. Scrum meeting/Daily standup.
Project reporting | Documentation | 6.5 | kl 0830-1500 | 2023-04-24 | Main report, Results.
Project reporting | Documentation | 2 | kl 1500 - 1700 | 2023-04-24 | Main report, planned and discusssed structure
Week 17 |  | 9
Timesheet |  | Birthe
Activity | Category | Duration (hours)
Team meetings | Adminstration | 0.5 | kl 0800-0830 | 2023-04-24 | Team meeting. Meeting with TA. Scrum meeting/Daily standup.
Project reporting | Documentation | 8.5 | kl 0830-1700 | 2023-04-24 | Main report, Methods
Project reporting | Documentation | 6 |  | 2023-04-25 | Main report, Methods + Discussion + edits
Project reporting | Final delivery
Project reporting | Final delivery
Week 17 |  | 15
Timesheet |  | Vemund
Activity | Category | Duration (hours)
Team meetings | Adminstration | 0.5 | ¦ | 2023-04-24 | Team meeting. Meeting with TA. Scrum meeting/Daily standup.
Coding | Quality assurance | 8.5 | kl 0830-1700 | 2023-04-24 | Quality assurance of code + Gitlab pages
Week 17 |  | 9
Timesheet |  | 0
Activity | Category | Duration (hours)
Week 17 |  | 0